## Overview
JOBPILOT — PROJECT PROGRESS TRACKER
Last reviewed: 09-Oct-2026 ¦ Update statuses as features are implemented and tested.
Area | Current status | Summary | Next action
Candidate account & profile | Completed / working | Registration/login, Google/GitHub OAuth, MongoDB user storage, profile APIs, profile completion, dashboard/current-user flow, Gateway access. | Regression-test critical flows before release.
Resume upload & vector retrieval | Working | GridFS/document metadata, upload event/outbox and consumer, service-authenticated document retrieval, embeddings and Qdrant retrieval reported working. | Verify resume replacement lifecycle and use of resume context in chat.
Conversational AI | Partially implemented | Spring AI/LLM integration exists; full orchestration, follow-up context and tool-driven job search are not verified end to end. | Audit existing chat implementation before adding classes.
LLM-assisted job discovery | In progress — scaffold unverified | Generic job models/provider architecture discussed; files and mock endpoint not confirmed compiling/running. | Verify existing files, compile, test mock endpoint, then implement LLM query planner.
External job providers | Not started | Adzuna credentials planned for later; no real provider integration confirmed. | Implement authorized provider adapter and check terms/quotas.
Job matching & skill gaps | Not started end to end | No verified pipeline ranks real jobs against candidate evidence or explains job-specific skill gaps. | Implement evidence-based matching and skill-gap analysis.
Learning & interview preparation | Not integrated | Study plans, learning resources, job-specific interview practice and progress tracking are incomplete. | Build after job matching is working.
API Gateway & security | Core security tested | Gateway routing, JWT validation, CORS, no-token/invalid-token 401s, valid-token access and JSON 401 response tested. | Standardize 403/400/404/500 responses across Gateway and backend.
React experience & production hardening | Partially implemented / remaining | UI exists; complete conversational workflow, job cards/resources and production operations not verified. | Integrate UI after backend workflow is stable.
Status definitions
Completed / working | Implemented and reported tested/working.
In progress | Implementation or verification is underway.
Not started | No implementation confirmed.
Scaffold unverified | Design/code was drafted, but file existence, compilation or end-to-end behavior is not confirmed.

## Detailed Tracker
DETAILED REQUIREMENT TRACKER
Edit Status, Progress %, Priority, Next action and Notes as work progresses.
Area | Requirement / task | Status | Progress % | Priority | Next action / acceptance criteria | Notes / evidence
Account & profile | Registration and username/password login | Completed / working | 100 | Medium | Regression-test register/login through Gateway. | Reported implemented and working.
Account & profile | Google/GitHub OAuth login | Completed / working | 100 | Medium | Regression-test callback and user create/update. | Previously tested; recheck during release testing.
Account & profile | User persistence in MongoDB | Completed / working | 100 | Medium | Verify user create/update paths. | Reported implemented.
Account & profile | Profile create/update and completion status | Completed / working | 100 | Medium | Verify partial and complete profile flows. | Reported implemented.
Account & profile | Dashboard/current-user flow | Completed / working | 100 | Medium | Verify protected calls use Gateway and JWT. | Reported implemented.
Resume | Resume upload and GridFS/document metadata | Completed / working | 100 | High | Test upload, retrieval and metadata consistency. | Reported implemented.
Resume | Upload event/outbox and AI consumer | Completed / working | 100 | High | Test event processing and failure behavior. | Reported implemented.
Resume | Service-authenticated document retrieval | Completed / working | 100 | High | Verify service token and document download. | Reported working.
Resume | Resume embeddings stored in Qdrant | Completed / working | 100 | High | Verify indexing for a newly uploaded resume. | Reported working.
Resume | Resume semantic retrieval | Completed / working | 100 | High | Verify relevant chunks for test queries. | Reported working.
Resume | Resume replacement lifecycle | Verification pending | 25 | High | Test replacement, old GridFS cleanup and metadata consistency. | Design discussed; full lifecycle not confirmed.
Resume & chat | Use resume/profile context in relevant chat turns | Not started / unverified | 10 | High | Verify answers use retrieved candidate evidence when relevant. | Retrieval works; integrated chat workflow not verified.
Chat | LLM chat response | Partially implemented | 40 | High | Run end-to-end technical Q&A with available model quota. | Spring AI integration exists; reliability needs verification.
Chat | Conversation history and follow-up context | Not started / unverified | 0 | High | Ask a follow-up referring to a prior job and verify context. | Not verified as complete.
Chat | Intent/tool orchestration from natural-language requests | Not started | 0 | High | Route chat to job search, matching, learning or direct Q&A. | Not implemented end to end.
Job discovery | JobListing common model | Scaffold unverified | 20 | High | Confirm file exists, compile and validate fields. | Code suggested; implementation not confirmed.
Job discovery | JobSearchRequest and JobSearchResponse | Scaffold unverified | 20 | High | Confirm files, validation, defaults and API contract. | Code suggested; implementation not confirmed.
Job discovery | JobSearchProvider and result model | Scaffold unverified | 20 | High | Compile interface and provider result contract. | Design/code discussed; not confirmed running.
Job discovery | Mock provider and sample search endpoint | Scaffold unverified | 10 | High | Enable mock locally and test endpoint through Gateway. | Sample data must be labeled mock, not real vacancies.
Job discovery | LLM query planner | Not started | 0 | High | Generate bounded structured queries from candidate context and chat intent. | Approach agreed; implementation not confirmed.
Job discovery | Adzuna provider integration | Not started | 0 | High | Add credentials via environment variables; parse results and pagination. | Credentials planned for later.
Job discovery | Additional authorized job providers | Not started | 0 | Medium | Implement adapters using shared provider contract. | Respect each provider's access terms.
Job discovery | Normalize and deduplicate real listings | Not started | 0 | High | Deduplicate listings while preserving source and application URLs. | Not complete.
Matching | Extract candidate skills and experience | Not started end to end | 10 | High | Combine structured profile with relevant resume evidence. | Resume retrieval foundation exists.
Matching | Rank real jobs by relevance | Not started | 0 | High | Return explainable ranking using job requirements and candidate evidence. | Not implemented.
Matching | Job-specific skill-gap analysis | Not started | 0 | High | Identify required, evidenced, missing and uncertain skills per job. | Not implemented.
Matching | Explain match and preserve job identity in follow-ups | Not started | 0 | High | Explain match and resolve references such as 'the second job'. | Not implemented.
Learning | Recommend study topics for a selected job | Not started | 0 | High | Generate a prioritized plan tied to verified job requirements. | Not implemented.
Learning | Retrieve relevant online resources | Not started | 0 | Medium | Return useful, valid links from permitted sources. | Not implemented.
Learning | Technical Q&A (Java/Spring/Kafka etc.) | Partially implemented | 35 | High | Validate answer quality, code examples and follow-up behavior. | LLM integration exists; complete feature needs verification.
Learning | Interview questions/mock interviews | Not started | 0 | Medium | Generate job-specific practice and evaluate candidate answers. | Not implemented.
Learning | Track progress against skill gaps | Not started | 0 | Low | Persist learning progress and update readiness over time. | Not implemented.
Gateway/security | Gateway routing and JWT validation | Completed / working | 100 | High | Retest public/protected endpoints after changes. | Tested.
Gateway/security | CORS through Gateway | Completed / working | 100 | High | Confirm no duplicate CORS headers after config changes. | Reported working.
Gateway/security | Standard JSON 401 response | Completed / working | 100 | Medium | Keep response contract stable. | Verified with curl.
Gateway/security | Standard JSON 403 response | Not started / unverified | 20 | Medium | Test authenticated user lacking permission; confirm consistent JSON. | Handler wiring suggested; not confirmed tested.
Gateway/security | Standardized 400/404/500 across backend and Gateway | Not started | 0 | Medium | Preserve downstream status and use common error schema. | Not complete.
Frontend | Chat interface connected to orchestrator | Not started end to end | 10 | High | Chat should invoke tools and display the right response. | UI exists; integrated workflow not verified.
Frontend | Job cards, match scores, gaps and application links | Not started | 0 | High | Display real source, title, company, match rationale and link. | Not implemented end to end.
Production | Provider timeout/retry/rate limit/cache | Not started | 0 | Medium | Protect API quota and handle provider failures. | Future hardening.
Production | Observability and correlation IDs | Not started | 0 | Low | Correlate requests/provider calls without leaking secrets. | Future hardening.
Production | End-to-end regression tests | In progress | 20 | High | Automate account, resume, Gateway and AI flows. | Gateway security tested manually.

## Roadmap
JOBPILOT IMPLEMENTATION ROADMAP
Phase | Focus | Status | Definition of done | Dependencies | Notes
1 | Foundation: account, profile, documents, Qdrant, Gateway | Mostly complete | Critical flows pass regression tests; resume context can be retrieved reliably. | Existing backend, UI, AI service | Avoid rebuilding working features; verify resume replacement and chat-context integration.
2 | LLM-assisted job discovery | Current priority | Generic search pipeline compiles; mock search works; LLM generates bounded queries; provider results normalized. | Spring AI, JobListing, JobSearchProvider | Adzuna credentials can be added later.
3 | Real external job providers | Not started | At least one authorized provider returns real listings with valid source/application URLs and pagination. | Phase 2 | Check provider terms, quotas and attribution.
4 | Job matching and skill gaps | Not started | Rank real jobs against candidate evidence and explain required/matched/missing skills. | Phases 2–3, resume retrieval | Keep explanations evidence-based.
5 | Conversational orchestration | Not complete | Chat selects resume retrieval, job search, matching, learning or direct Q&A; follow-ups retain context. | Phases 2–4, existing LLM chat | Extend existing chat code after auditing it.
6 | Learning and interview preparation | Not started | Provide job-specific study plans, valid learning links, technical explanations and interview practice. | Phases 4–5 | Technical Q&A can work independently of job search.
7 | React career-assistant UX | Partially implemented | Chat displays real job cards, match explanations, skill gaps, resources and follow-up context. | Phases 2–6 | UI exists; full workflow not verified.
8 | Production hardening | Partially complete | Consistent errors, tests, timeouts, retries, quotas, caching, observability and secret management. | All feature phases | Gateway JWT/CORS basics already tested.

## Update Log
PROGRESS UPDATE LOG
Add one row whenever you implement or verify a meaningful change.
Date | Area / task | Change or test performed | Result / evidence | Next step